## LAT Operations
System Safety Assessment - Large Airtanker Program
Large Airtanker Program System - Airworthiness
|  | Pre Mitigation |  |  | Mitigation | Post Mitigation
Sub-systems | Hazards | Likelihood | Severity | Outcome |  | Likelihood | Severity | Outcome | Mitigation Achieved? Yes or No | Additional Local Mitigation | Post Mitigation Value
Continued Airworthiness | Previous aircraft use/maintenance programs did not compensate for structural loads experienced during the fire mission. | Occasional | Catastrophic | High | Continue utilizing USFS Continued Airworthiness Program, in association with contractual requirements and industry standards required by FAR 25.571. Incorporate the latest inspection technology. | Remote | Critical | Medium
| Load limit exceedance. | Occasional | Critical | Serious | Maintain a load monitoring system, utilizing the latest inspection technology. Maintain routine (daily) inspection program. | Improbable | Critical | Medium
| Engine failures. | Probable | Critical | High | Follow prescribed schedule for engine maintenance and overhaul. Reduce overhaul intervals. | Remote | Marginal | Medium
Airframe Fatigue Damage | Significant exposure to airframe stresses in the firefighting mission profile poses additional fatigue factors that shorten airframe life expectancy. | Frequent | Catastrophic | Serious | Perform Damage Tolerance and Fatigue (DT&F) analysis in accordance with 14 CFR 25.571 for the tanker mission and require inspection programs and life limits based on that analysis. | Remote | Marginal | Medium
Large Airtanker Program System - Contracts
|  | Pre Mitigation |  |  | Mitigation | Post Mitigation
Sub-systems | Hazards | Likelihood | Severity | Outcome |  | Likelihood | Severity | Outcome | Mitigation Achieved? Yes or No | Additional Local Mitigation | Post Mitigation Value
Contract Management | Unfamiliar with exclusive use vs call-when-needed. | Frequent | Marginal | Serious | Educate dispatch centers, ATBMs, and fire management on the differences between the contract types and ordering processes. Provide contracts to all end users, regardless of agency. Ensure CORs and COs are available for questions from end users. | Occasional | Negligible | Low
| Not enough CORs to manage contract line items. | Frequent | Marginal | Serious | Encourage more aviation-specific COR training. Provide information and assistance on becoming a COR for LAT/VLAT contracts, regardless of agency. Devleop an incentive program for the CORs additonal duties. | Occasional | Marginal | Medium
| Lack of "home bases" may affect quality and timeliness of maintenance on aircraft. | Probable | Catastrophic | High | Ensure contractors have a maintenance area for required scheduled maintenance, inspections/overhauls of engines and aircraft components. Coordinate with maintenance inspectors on all unscheduled maintenance. Assist contractors with obtaining airport security clearance for working overnight at airports. | Remote | Critical | Medium
Large Airtanker Program System - Operations
|  | Pre Mitigation |  |  | Mitigation | Post Mitigation
Sub-systems | Hazards | Likelihood | Severity | Outcome |  | Likelihood | Severity | Outcome | Mitigation Achieved? Yes or No | Additional Local Mitigation | Post Mitigation Value
Management Decisions | Inefficient use of airtankers may result in unnecessary risk exposure to aircrew and ground personnel (risk vs. gain). | Probable | Critical | High | Pilots, fire management, dispatchers, aerial supervisors and line personnel need proper training on effective use of aircraft. Conduct pre- and post-flight briefings; use AARs as mitigation to prevent accidents. Review incident objectives and adjust tactics as necessary. In extreme weather, set aircraft down until conditions improve. | Occasional | Marginal | Medium
| A sense of urgency may be placed on crew at various points during the mission. | Probable | Critical | High | Address "safety" vs. "urgency" at crew in-briefing with contractor and agency employees. Review "How to Refuse Risk" with crew. Reinforce this throughout operational periods. Ensure adequate flight planning occurs prior to take off. | Remote | Critical | Medium
Mission Environment | CFIT due to low level operations. | Frequent | Catastrophic | High | Perform high-level recon prior to descending to drop height/low-level environment. Utilize aerial supervision and/or leadplane when available. Manage radio communication (sterile cockpit during drop). Reduce time in low-level environment. Ensure aircraft do not go below minimum drop height. | Remote | Critical | Medium
| Mountainous terrain. | Frequent | Catastrophic | High | Ensure pilots are trained, experienced and carded/qualified for the mission. Flight crews obtain thorough briefings on local conditions before starting operations. | Occasional | Critical | Serious
| Weather: poor visibility, thunderstorms, hot/high DA, turbulence. | Frequent | Catastrophic | High | Obtain most current/accurate weather forecast for airport and fire area. Conduct pre-mission risk assessment to determine mission hazards, restrictions and mitigations. Delay mission until conditions improve. Follow policy on visibility, wind speed updating load calcs, etc. Establish trigger points to stop operations. | Remote | Critical | Medium
Airspace | Flying in special use areas (MTRs, TFRs, restricted airspace). | Probable | Catastrophic | High | Ensure dispatchers have contacted the military for clearance into restricted areas and have completed airspace deconfliction. Transmit appropriate squawk codes. Practice see and avoid. Be aware of private aircraft in TFR area. Utilize aerial supervision when available.Refer to local base plan for specific SUA procedures. | Occasional | Marginal | Medium
| Congested areas and urban interface. | Probable | Catastrophic | High | Comply with congested area policies in NWCG Standards for Aerial Supervision and ensure that aerial supervision is in place or has been ordered. | Remote | Critical | Medium
Retardant Loading | Fatigue of aircrew during hot loading and simultaneous fueling and loading operations (less time out of the cockpit) | Frequent | Critical | High | One crewmember should stand up or leave cockpit when possible. Rotate crewmembers when they need food/fuel/water. Open door (on opposite side of running engines while hot loading) for fresh air. Consider alternating simultaneous fueling/loading operation with normal fueling/loading operation to provide a longer break outside of aircraft for all crewmembers. | Occasional | Critical | Serious
| Overfilling and mixing errors. | Occasional | Critical | Serious | Ensure all airtankers are loaded using a mass flow meter. Vendor and government personnel review and follow mixing and loading procedures. | Remote | Marginal | Medium
Large Airtanker Program System - Human Factors
|  | Pre Mitigation |  |  | Mitigation | Post Mitigation
Sub-systems | Hazards | Likelihood | Severity | Outcome |  | Likelihood | Severity | Outcome | Mitigation Achieved? Yes or No | Additional Local Mitigation | Post Mitigation Value
Pilot Proficiency and Training | Lack of fire mission training and lack of proficiency flight time. | Probable | Catastrophic | High | Ensure vendors utilize training programs such as CRM, risk management, and flight safety with the intent to standardize cockpit procedures. Provide NAFA training often to capture new pilots and allow for refresher training of all pilots. Provide adequate training opportunities with experienced pilots within the fire environment. Ensure adequate proficiency flight time is provided prior to starting on contract. During the contract period, vendors are responsibile to ensure their pilots are proficient. | Occasional | Critical | Serious
Mission Induced Stress | The limited number of airtankers has resulted in more frequent travel and change of duty station, which increases stress and has a negative effect on crew quality of life. | Frequent | Critical | High | Provide additional administrative support. Adhere to duty limits; implement Phase Duty Limitations as appropriate. Improve the management model for national deployment of the fleet. Add more airtankers. | Occasional | Critical | Serious
| Target fixation and tactical maneuvering errors. | Probable | Catastrophic | High | Address airtanker pilot training and proficiency to reduce frequency of accidents. Ensure aircraft performance planning for successful outcome in a high rate of descent, level off, and climb out profile. Provide adequate training time in fire environment. | Occasional | Critical | Serious
Human Factors | Acceptance of high risk missions as normal. | Frequent | Catastrophic | High | Review existing policy/procedures and risk assessment during in-brief and mission briefings. Utilize risk management tools, including Go/No-Go checklists. Educate personnel on the normalization of risk and complacency. Make mission decisions at the appropriate level. Ensure communication between operations and aviation personnel. Emphasize importance of "situational awareness" as a means for recognizing risk. | Remote | Catastrophic | Serious
| Pilot/crew fatigue | Probable | Critical | High | Adhere to work/rest guidelines. Utilize interim flight and duty limitations/additional days off as authorized. Request personnel swap or additional crew members during peak fire activity. Ensure adequate pilot rest areas are available. | Remote | Critical | Medium
Large Airtanker Program System - Policy, Procedure, and Administration
|  | Pre Mitigation |  |  | Mitigation | Post Mitigation
Sub-systems | Hazards | Likelihood | Severity | Outcome |  | Likelihood | Severity | Outcome | Mitigation Achieved? Yes or No | Additional Local Mitigation | Post Mitigation Value
Agency Culture | ATBMs, users, contractors don't have full understanding of agency policies and procedures at different bases. | Probable | Critical | High | Ensure all users have access to Interagency policy and procedures. Follow SABO. Ensure communication between agencies. Attend the national ATBM workshop every three years. | Remote | Marginal | Medium
| "Can do" philosophy has fostered aviation programs with high risk operations. | Probable | Critical | High | Provide program oversight to assure risk is at lowest practicable level. Improve crew risk management. | Remote | Marginal | Medium
Large Airtanker Program System - Policy, Procedure, and Administration (continued)
|  | Pre Mitigation |  |  | Mitigation | Post Mitigation
Sub-systems | Hazards | Likelihood | Severity | Outcome |  | Likelihood | Severity | Outcome | Mitigation Achieved? Yes or No | Additional Local Mitigation | Post Mitigation Value
Quality Assurance and Inspections | Operator's lack of quality assurance and inspection program results in non compliance with contract airworthiness standards. | Probable | Critical | High | Enforce QA program for improved oversight of the contracted fleet. | Remote | Marginal | Medium
Large Airtanker Program System - Technology
|  | Pre Mitigation |  |  | Mitigation | Post Mitigation
Sub-systems | Hazards | Likelihood | Severity | Outcome |  | Likelihood | Severity | Outcome | Mitigation Achieved? Yes or No | Additional Local Mitigation | Post Mitigation Value
Human Aided Technology | HAT underutilized resulting in task saturation. | Occasional | Marginal | Medium | Develop new technologies for the mission such as glass cockpit, synthetic vision, electronic target identification, laser targeting, etc. Utilize updated electronic equipment if possible [e.g. Traffic Collision Avoidance System (TCAS) and Automatic Dependent Surveillance-Broadcast in (ADS-B in)]. | Occasional | Negligible | Low